## Effort -backup (hidden)
Customer: |  |  | CarzOnRent |  | Effort | 308.0782 | PD
[6 empty] | 14.3292 | PM
|  |  | 21.5 |  |  | 0.1 | 0.4
Estimate
|  | # | Features | UI Design | Dev | UT | Web services Validation & Integration | Comments
|  | 1 | Req validation |  | 5 |  |  | Onsite
|  | 2 | App Arch & BE integration Design |  | 5
|  |  | Login | 1 | 1 | 0.2 | 0.8 | ? Required since card details are stored
|  | 3 | Home
|  | 3.1 | Current booking, Booking Status, Favorite trips, Payment, Book Later, other features to redirect to website, Settings | 1 | 1 | 0.2 | 0
|  | 4 | Current booking
|  | 4.1 | Maps with cabs around user | 1 | 2 | 0.3 | 1.2
|  | 4.2 | Book Now | 0.5 | 1 | 0.225 | 0.6
|  | 4.2.1 | Booking confirmation (via notifications/SMS ?) | 0.25 | 0.5 | 0.1125 | 0.3
|  | 4.2.2 | Booking Status | 0.5 | 1 | 0.225 | 0.6
|  | 4.3 | Maps with allocated cab's location | 1 | 2 | 0.45 | 1.2
|  | 4.3.1 | Finding the shortest route from cab to current location | 0.25 | 1 | 0.1875 | 0.5 | ?
|  | 4.4 | Book History? (auto sort on location / timeline) | 1 | 2 | 0.3 | 1.2
|  | 4.4.1 | create a booking based on a previous booking
|  | 4.5 | Sharing on FB | 0.25 | 1 | 0.1875 | 0.5
|  | 4.6 | Sharing on TWT | 0.25 | 1 | 0.1875 | 0.5
|  | 5 | Booking Status | 1 | 2 | 0.3 | 1.2
|  | 6 | Payment | 1 | 2 | 0.45 | 0.3675 | Invoke Payment API exposed by BE
|  | 6.1 | Setup (Store Card info in BE via API) | 1 | 2 | 0.45 | 0.49
|  | 7 | Book Later | 2 | 5 | 0.7 | 1.14 | Is the difference only about lead time of booking a cab? Need more info
|  | 8 | Favorite trips ( for Book later trips)
|  |  | List | 0.5 | 1 | 0.225 | 0.6
|  |  | Detail view | 0.5 | 1.5 | 0.3 | 0.8
|  |  | Book | 0.25 | 0.5 | 0.1125 | 0.3
|  | 9 | Redirect to Mobile website | 0.5 | 0.5 | 0.1 | 0
Booking outstation cab
Booking local cab
Booking self driven cab
Booking international cab
|  | 10 | Settings | 0.5 | 1 | 0.15 | 0.6
Do not prompt to connect to GPS
|  |  | Card list | 0.5 | 1
Save address
|  |  | Total effort | 14.75 | 40 | 5.3625 | 12.8975
|  | 11 | Dev effort Summary
|  |  | iPhone | 14.75 | 40 | 5.3625 | 12.8975
|  |  |  | 0.5 | 0.15
|  |  | iPad | 3.6875 | 6 | 5.3625 | 0
|  |  | Android Phone | 7.375 | 40 | 5.3625 | 12.8975
|  |  | Android Tablets | 3.6875 | 6 | 5.3625 | 0
|  |  | APNS setup |  | 1 | 0.1 | 0.4
|  |  | GCM setup |  | 1 | 0.1 | 0.4
|  |  | Total Dev effort | 172.395
|  | 12 | Testing
| 0.3 |  | Phones | 42.4935
| 0.15 |  | Tablets | 4.515
|  | 13 | UAT (2 weeks) | 10
|  | 14 | App Store: support for issues(2 weeks) | 10
|  | 15 | Go-Live support ( 2 weeks) -offshore | 10
|  | 16 | Traveling costs (to be included)
|  | 17 | Project Management | 27.9404 |  |  |  | 10%
|  | 18 | Contingency | 30.7344 |  |  |  | 10%
|  | 19 | Grand total - effort | 308.0782 |  |  |  | person days
|  |  |  | 14.3292 |  |  |  | person month
Assumptions
|  | 1 | Web services development effort are not included; They expected to be provided by CarzonRent
|  | 2 | Apple's Dev subscription is to be subscribed by CarzonRent
|  | 3 | Icons & Images will be provided by CarzonRent
4

## ResLoad-wrk (hidden)
| Mar | Apr | May | Jun | Jul
B1 | 136 | 112 | 8 | 40 | 24
B2 | 56 | 160 | 24
B3 | 56 | 160 | 24
C1 | 136 |  | 32 | 168 | 24
C2 | 96
BC1 | 80
BB1 | 80
B4 | 56 | 160 | 24
B5 | 56 | 160 | 24
B6 | 56 | 160 | 24
C3 |  | 112 | 8
C4 |  | 8 | 184 | 128
B7 |  | 8 | 152
B8 |  | 8 | 152
C5 | 56 | 160 | 24
C6 | 56 | 160 | 24
| Mar | Apr | May | Jun | Jul |  | Mar | Apr | May | Jun | Jul
B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15 | B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15
B2 | 0.35 | 1 | 0.15 | 0 | 0 | B2 | 0.35 | 1 | 0.15 | 0 | 0
B3 | 0.35 | 1 | 0.15 | 0 | 0 | B3 | 0.35 | 1 | 0.15 | 0 | 0
C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15 | C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15
C2 | 0.6 | 0 | 0 | 0 | 0 | C2 | 0.6 | 0 | 0 | 0 | 0
BC1 | 0.5 | 0 | 0 | 0 | 0 | BC1 | 0.5 | 0 | 0 | 0 | 0
BB1 | 0.5 | 0 | 0 | 0 | 0 | BB1 | 0.5 | 0 | 0 | 0 | 0
B4 | 0.35 | 1 | 0.15 | 0 | 0 | B4 | 0.35 | 1 | 0.15 | 0 | 0
B5 | 0.35 | 1 | 0.15 | 0 | 0 | B5 | 0.35 | 1 | 0.15 | 0 | 0
B6 | 0.35 | 1 | 0.15 | 0 | 0 | B6 | 0.35 | 1 | 0.15 | 0 | 0
C3 | 0 | 0.7 | 0.05 | 0 | 0 | C3 | 0 | 0.7 | 0.05 | 0 | 0
C4 | 0 | 0.05 | 1.15 | 0.8 | 0 | C4 | 0 | 0.05 | 1.15 | 0.8 | 0
B7 | 0 | 0.05 | 0.95 | 0 | 0 | B7 | 0 | 0.05 | 0.95 | 0 | 0
B8 | 0 | 0.05 | 0.95 | 0 | 0 | B8 | 0 | 0.05 | 0.95 | 0 | 0
C5 | 0.35 | 1 | 0.15 | 0 | 0 | C5 | 0.35 | 1 | 0.15 | 0 | 0
C6 | 0.35 | 1 | 0.15 | 0 | 0 | C6 | 0.35 | 1 | 0.15 | 0 | 0
PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rolled up
[7 empty] | Mar | Apr | May | Jun | Jul |  |  | Mar | Apr | May | Jun | Jul |  |  | Mar | Apr | May | Jun | Jul
[6 empty] | B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15 | iOS Dev | B1-B6 | 2.6 | 5.7 | 0.8 | 0.25 | 0.15 | iOS Dev | B1-B6 | 2.5 | 5 | 1 | 0.25 | 0.5
[6 empty] | B2 | 0.35 | 1 | 0.15 | 0 | 0 | iOS Sr. Dev | C1-C2, 5,6 | 2.15 | 2 | 0.5 | 1.05 | 0.15 | UX Dev | C1 | 0.5
[6 empty] | B3 | 0.35 | 1 | 0.15 | 0 | 0 | Tester | B7-8 | 0 | 0.1 | 1.9 | 0 | 0 | iOS Sr. Dev | C1-C3, 5,6 | 1.5 | 2 | 0.5 | 1 | 0.5
[6 empty] | C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15 | Sr. Tester | C4 | 0 | 0.05 | 1.15 | 0.8 | 0 | Tester | B7-8 | 0 | 0 | 1 | 0 | 0
[6 empty] | C2 | 0.6 | 0 | 0 | 0 | 0 | B/e Dev | BB1 | 0.5 | 0 | 0 | 0 | 0 | Sr. Tester | C4 | 0 | 0 | 1 | 1 | 0
[6 empty] | BC1 | 0.5 | 0 | 0 | 0 | 0 | B/e Sr. Dev | BC1, C3 | 0.5 | 0.7 | 0.05 | 0 | 0 | B/e Dev | BB1 | 0.5 | 0 | 0 | 0 | 0
[6 empty] | BB1 | 0.5 | 0 | 0 | 0 | 0 | PM |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | B/e Sr. Dev | BC1, C3 | 0.5 | 1 | 0 | 0 | 0
[6 empty] | B4 | 0.35 | 1 | 0.15 | 0 | 0 | [7 empty] | PM |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[6 empty] | B5 | 0.35 | 1 | 0.15 | 0 | 0 | [6 empty] | 23.6 | [6 empty] | 22.75
[6 empty] | B6 | 0.35 | 1 | 0.15 | 0 | 0
[6 empty] | C3 | 0 | 0.7 | 0.05 | 0 | 0 | [9 empty] | 6 | 8.5 | 4 | 2.75 | 1.5
[6 empty] | C4 | 0 | 0.05 | 1.15 | 0.8 | 0
[6 empty] | B7 | 0 | 0.05 | 0.95 | 0 | 0
[6 empty] | B8 | 0 | 0.05 | 0.95 | 0 | 0 |  |  | 2012-03-05 | Week1
[6 empty] | C5 | 0.35 | 1 | 0.15 | 0 | 0 |  |  | 2012-03-12 | Week2
[6 empty] | C6 | 0.35 | 1 | 0.15 | 0 | 0 |  |  | 2012-03-19 | Week3
[6 empty] | PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 2012-03-26 | Week4
[14 empty] | 2012-04-02 | Week5
[14 empty] | 2012-04-09 | Week6
[14 empty] | 2012-04-16 | Week7
[14 empty] | 2012-04-23 | Week8
[14 empty] | 2012-04-30 | Week9
[14 empty] | 2012-05-07 | Week10
[14 empty] | 2012-05-14 | Week11
[14 empty] | 2012-05-21 | Week12
[14 empty] | 2012-05-28 | Week13
[14 empty] | 2012-06-04 | Week14
[14 empty] | 2012-06-11 | Week15
[14 empty] | 2012-06-18 | Week16
[14 empty] | 2012-06-25 | Week17
[14 empty] | 2012-07-02 | Week18
[14 empty] | 2012-07-09 | Week19
[14 empty] | 2012-07-16 | Week20
[14 empty] | 2012-07-23 | Week21
[14 empty] | 2012-07-30 | Week22
[14 empty] | 2012-08-06 | Week23
Formulas:
Mar = [Mar, row above]+7

## Effort-Phase 1
Customer: |  |  | SageOne |  | Effort | 89.68 | PD
[6 empty] | 4.1712 | PM
|  |  | 21.5 |  |  | 0.2 | 0.4
Estimate
|  | # | Features | UI Design (Wireframes+Artwork) | Dev | UT | Web services Validation & Integration | Comments
|  | 1 | Req validation |  | 2
|  | 2 | Design
|  | 2.1 | Local Storage |  | 1
|  | 2.2 | Sage One server integration |  | 1
|  | 2.3 | Support multiple set of API's |  | 2
|  | 2.4 | Localization support |  | 1
|  | 2.5 | UI Navigation |  | 0.5
|  | 3 | Dashboard |  | 2 | 0.4 | 0.8
|  | 3.1 | Sign in using Sage Id |  | 2 | 0.4 | 0.8 | Reuse the existing components from Sage Mobile Sales
|  | 3.2 | Display company data (YTD income, YTD expense, YTD profit, no of outstanding invoices) |  | 2 | 0.4 | 0.8
|  | 3.3 | Option to switch company |  | 1 | 0.2
|  | 4 | Contacts
|  | 4.1 | Display contact list |  | 2 | 0.4 | 0.8
|  | 4.2 | Filter contact list |  | 1 | 0.2
|  | 4.3 | Display contact details |  | 1 | 0.2 | 0.4
|  | 4.4 | Add/Edit contact |  | 3 | 0.6 | 1.2
|  | 5 | Invoices
|  | 5.1 | Display inovice list |  | 2 | 0.4 | 0.8
|  | 5.2 | Filter invoice list |  | 1 | 0.2
|  | 5.3 | Display invoice details |  | 2 | 0.4 | 0.8
|  | 5.4 | Add/Edit invoice |  | 4 | 0.8 | 1.6
|  | 5.5 | View and email pdf of the invoice |  | 3 | 0.6
|  | 6 | Nice to have Features
|  | 6.1 | Update the contact details from map/current GPS location |  | 3 | 0.6
|  | 6.2 | Call the contact from contact detail view |  | 1 | 0.2
|  | 6.3 | Expenses
|  | 6.3.1 | Capture photo of the receipt and upload to users google drive |  | 3 | 0.6 | 1.2
|  | 6.3.2 | Option to choose the country |  | 1 | 0.2 |  | Our Suggestion: We can restrict the countries on the app store based on the apple id (Not user's locale). When the app is launched for the first time, we can seed the app using the user's locale.
|  |  | Total effort |  | 41.5 | 6.8 | 9.2
|  | 7 | Dev effort Summary
|  |  | iPhone |  | 41.5 | 6.8 | 9.2
|  |  | Total Dev effort |  | 57.5
| 0.2 | 8 | Testing |  | 11.5
|  | 9 | UAT (1 week) |  | 5
|  | 10 | App Store and Go Live Support |  | 2
|  | 11 | Project Management |  | 6.08 |  |  | 8%
|  | 12 | Contingency |  | 7.6 |  |  | 10%
|  | 13 | Grand total - effort |  | 89.68 |  |  | person days
[5 empty] | 4.1712 |  |  | person month
Assumptions
|  | 1 | Authentication is using Sage ID. Google Id is not considered
|  | 2 | The UX is provided by Sage. The estimate does not include UX effort
|  | 3 | The estimate is only for iPhone platform
|  | 4 | The app will be designed to support different Sage One API. However the estimate only inlcudes development for UK. The rest of the world development effort is not considered at this point
|  | 5 | The effort does not include any web service API development.
|  | 6 | The app will be supported for iOS 7 only
|  | 7 | The app will be supported for portrait orientation only
|  | 8 | Any delay in the UX, API details from Sage will impact the cost and schedule

## ResourceLoading-Phase1
Name of the client: SageOne
Resources | Grade |  | M1 | M2
BA | C |  |  |  | 0
Architect | D |  | 0.5 |  | 0.5 | B | 1.5
UX Designer | C | UI |  |  | 0 | C | 2
iOS Lead/Sr. Dev | C |  | 0.5 | 1 | 1.5 | D | 0.8
iOS Developer | B | Dev & UT | 0.5 | 1 | 1.5
Sr. Tester | C |  |  | 0.5 | 0.5
Tester | B | Intg Testing |  |  | 0
PM | D | PM | 0.2 | 0.1 | 0.3
4.3
Note on F1: Offshore rate applies