## Effort -backup (hidden)
Customer: |  |  | CarzOnRent |  | Effort | 308.0782 | PD
[6 empty] | 14.3292 | PM
|  |  | 21.5 |  |  | 0.1 | 0.4
Estimate
|  | # | Features | UI Design | Dev | UT | Web services Validation & Integration | Comments
|  | 1 | Req validation |  | 5 |  |  | Onsite
|  | 2 | App Arch & BE integration Design |  | 5
|  |  | Login | 1 | 1 | 0.2 | 0.8 | ? Required since card details are stored
|  | 3 | Home
|  | 3.1 | Current booking, Booking Status, Favorite trips, Payment, Book Later, other features to redirect to website, Settings | 1 | 1 | 0.2 | 0
|  | 4 | Current booking
|  | 4.1 | Maps with cabs around user | 1 | 2 | 0.3 | 1.2
|  | 4.2 | Book Now | 0.5 | 1 | 0.225 | 0.6
|  | 4.2.1 | Booking confirmation (via notifications/SMS ?) | 0.25 | 0.5 | 0.1125 | 0.3
|  | 4.2.2 | Booking Status | 0.5 | 1 | 0.225 | 0.6
|  | 4.3 | Maps with allocated cab's location | 1 | 2 | 0.45 | 1.2
|  | 4.3.1 | Finding the shortest route from cab to current location | 0.25 | 1 | 0.1875 | 0.5 | ?
|  | 4.4 | Book History? (auto sort on location / timeline) | 1 | 2 | 0.3 | 1.2
|  | 4.4.1 | create a booking based on a previous booking
|  | 4.5 | Sharing on FB | 0.25 | 1 | 0.1875 | 0.5
|  | 4.6 | Sharing on TWT | 0.25 | 1 | 0.1875 | 0.5
|  | 5 | Booking Status | 1 | 2 | 0.3 | 1.2
|  | 6 | Payment | 1 | 2 | 0.45 | 0.3675 | Invoke Payment API exposed by BE
|  | 6.1 | Setup (Store Card info in BE via API) | 1 | 2 | 0.45 | 0.49
|  | 7 | Book Later | 2 | 5 | 0.7 | 1.14 | Is the difference only about lead time of booking a cab? Need more info
|  | 8 | Favorite trips ( for Book later trips)
|  |  | List | 0.5 | 1 | 0.225 | 0.6
|  |  | Detail view | 0.5 | 1.5 | 0.3 | 0.8
|  |  | Book | 0.25 | 0.5 | 0.1125 | 0.3
|  | 9 | Redirect to Mobile website | 0.5 | 0.5 | 0.1 | 0
Booking outstation cab
Booking local cab
Booking self driven cab
Booking international cab
|  | 10 | Settings | 0.5 | 1 | 0.15 | 0.6
Do not prompt to connect to GPS
|  |  | Card list | 0.5 | 1
Save address
|  |  | Total effort | 14.75 | 40 | 5.3625 | 12.8975
|  | 11 | Dev effort Summary
|  |  | iPhone | 14.75 | 40 | 5.3625 | 12.8975
|  |  |  | 0.5 | 0.15
|  |  | iPad | 3.6875 | 6 | 5.3625 | 0
|  |  | Android Phone | 7.375 | 40 | 5.3625 | 12.8975
|  |  | Android Tablets | 3.6875 | 6 | 5.3625 | 0
|  |  | APNS setup |  | 1 | 0.1 | 0.4
|  |  | GCM setup |  | 1 | 0.1 | 0.4
|  |  | Total Dev effort | 172.395
|  | 12 | Testing
| 0.3 |  | Phones | 42.4935
| 0.15 |  | Tablets | 4.515
|  | 13 | UAT (2 weeks) | 10
|  | 14 | App Store: support for issues(2 weeks) | 10
|  | 15 | Go-Live support ( 2 weeks) -offshore | 10
|  | 16 | Traveling costs (to be included)
|  | 17 | Project Management | 27.9404 |  |  |  | 10%
|  | 18 | Contingency | 30.7344 |  |  |  | 10%
|  | 19 | Grand total - effort | 308.0782 |  |  |  | person days
|  |  |  | 14.3292 |  |  |  | person month
Assumptions
|  | 1 | Web services development effort are not included; They expected to be provided by CarzonRent
|  | 2 | Apple's Dev subscription is to be subscribed by CarzonRent
|  | 3 | Icons & Images will be provided by CarzonRent
4

## ResLoad-wrk (hidden)
| Mar | Apr | May | Jun | Jul
B1 | 136 | 112 | 8 | 40 | 24
B2 | 56 | 160 | 24
B3 | 56 | 160 | 24
C1 | 136 |  | 32 | 168 | 24
C2 | 96
BC1 | 80
BB1 | 80
B4 | 56 | 160 | 24
B5 | 56 | 160 | 24
B6 | 56 | 160 | 24
C3 |  | 112 | 8
C4 |  | 8 | 184 | 128
B7 |  | 8 | 152
B8 |  | 8 | 152
C5 | 56 | 160 | 24
C6 | 56 | 160 | 24
| Mar | Apr | May | Jun | Jul |  | Mar | Apr | May | Jun | Jul
B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15 | B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15
B2 | 0.35 | 1 | 0.15 | 0 | 0 | B2 | 0.35 | 1 | 0.15 | 0 | 0
B3 | 0.35 | 1 | 0.15 | 0 | 0 | B3 | 0.35 | 1 | 0.15 | 0 | 0
C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15 | C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15
C2 | 0.6 | 0 | 0 | 0 | 0 | C2 | 0.6 | 0 | 0 | 0 | 0
BC1 | 0.5 | 0 | 0 | 0 | 0 | BC1 | 0.5 | 0 | 0 | 0 | 0
BB1 | 0.5 | 0 | 0 | 0 | 0 | BB1 | 0.5 | 0 | 0 | 0 | 0
B4 | 0.35 | 1 | 0.15 | 0 | 0 | B4 | 0.35 | 1 | 0.15 | 0 | 0
B5 | 0.35 | 1 | 0.15 | 0 | 0 | B5 | 0.35 | 1 | 0.15 | 0 | 0
B6 | 0.35 | 1 | 0.15 | 0 | 0 | B6 | 0.35 | 1 | 0.15 | 0 | 0
C3 | 0 | 0.7 | 0.05 | 0 | 0 | C3 | 0 | 0.7 | 0.05 | 0 | 0
C4 | 0 | 0.05 | 1.15 | 0.8 | 0 | C4 | 0 | 0.05 | 1.15 | 0.8 | 0
B7 | 0 | 0.05 | 0.95 | 0 | 0 | B7 | 0 | 0.05 | 0.95 | 0 | 0
B8 | 0 | 0.05 | 0.95 | 0 | 0 | B8 | 0 | 0.05 | 0.95 | 0 | 0
C5 | 0.35 | 1 | 0.15 | 0 | 0 | C5 | 0.35 | 1 | 0.15 | 0 | 0
C6 | 0.35 | 1 | 0.15 | 0 | 0 | C6 | 0.35 | 1 | 0.15 | 0 | 0
PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rolled up
[7 empty] | Mar | Apr | May | Jun | Jul |  |  | Mar | Apr | May | Jun | Jul |  |  | Mar | Apr | May | Jun | Jul
[6 empty] | B1 | 0.85 | 0.7 | 0.05 | 0.25 | 0.15 | iOS Dev | B1-B6 | 2.6 | 5.7 | 0.8 | 0.25 | 0.15 | iOS Dev | B1-B6 | 2.5 | 5 | 1 | 0.25 | 0.5
[6 empty] | B2 | 0.35 | 1 | 0.15 | 0 | 0 | iOS Sr. Dev | C1-C2, 5,6 | 2.15 | 2 | 0.5 | 1.05 | 0.15 | UX Dev | C1 | 0.5
[6 empty] | B3 | 0.35 | 1 | 0.15 | 0 | 0 | Tester | B7-8 | 0 | 0.1 | 1.9 | 0 | 0 | iOS Sr. Dev | C1-C3, 5,6 | 1.5 | 2 | 0.5 | 1 | 0.5
[6 empty] | C1 | 0.85 | 0 | 0.2 | 1.05 | 0.15 | Sr. Tester | C4 | 0 | 0.05 | 1.15 | 0.8 | 0 | Tester | B7-8 | 0 | 0 | 1 | 0 | 0
[6 empty] | C2 | 0.6 | 0 | 0 | 0 | 0 | B/e Dev | BB1 | 0.5 | 0 | 0 | 0 | 0 | Sr. Tester | C4 | 0 | 0 | 1 | 1 | 0
[6 empty] | BC1 | 0.5 | 0 | 0 | 0 | 0 | B/e Sr. Dev | BC1, C3 | 0.5 | 0.7 | 0.05 | 0 | 0 | B/e Dev | BB1 | 0.5 | 0 | 0 | 0 | 0
[6 empty] | BB1 | 0.5 | 0 | 0 | 0 | 0 | PM |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | B/e Sr. Dev | BC1, C3 | 0.5 | 1 | 0 | 0 | 0
[6 empty] | B4 | 0.35 | 1 | 0.15 | 0 | 0 | [7 empty] | PM |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
[6 empty] | B5 | 0.35 | 1 | 0.15 | 0 | 0 | [6 empty] | 23.6 | [6 empty] | 22.75
[6 empty] | B6 | 0.35 | 1 | 0.15 | 0 | 0
[6 empty] | C3 | 0 | 0.7 | 0.05 | 0 | 0 | [9 empty] | 6 | 8.5 | 4 | 2.75 | 1.5
[6 empty] | C4 | 0 | 0.05 | 1.15 | 0.8 | 0
[6 empty] | B7 | 0 | 0.05 | 0.95 | 0 | 0
[6 empty] | B8 | 0 | 0.05 | 0.95 | 0 | 0 |  |  | 2012-03-05 | Week1
[6 empty] | C5 | 0.35 | 1 | 0.15 | 0 | 0 |  |  | 2012-03-12 | Week2
[6 empty] | C6 | 0.35 | 1 | 0.15 | 0 | 0 |  |  | 2012-03-19 | Week3
[6 empty] | PM | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 2012-03-26 | Week4
[14 empty] | 2012-04-02 | Week5
[14 empty] | 2012-04-09 | Week6
[14 empty] | 2012-04-16 | Week7
[14 empty] | 2012-04-23 | Week8
[14 empty] | 2012-04-30 | Week9
[14 empty] | 2012-05-07 | Week10
[14 empty] | 2012-05-14 | Week11
[14 empty] | 2012-05-21 | Week12
[14 empty] | 2012-05-28 | Week13
[14 empty] | 2012-06-04 | Week14
[14 empty] | 2012-06-11 | Week15
[14 empty] | 2012-06-18 | Week16
[14 empty] | 2012-06-25 | Week17
[14 empty] | 2012-07-02 | Week18
[14 empty] | 2012-07-09 | Week19
[14 empty] | 2012-07-16 | Week20
[14 empty] | 2012-07-23 | Week21
[14 empty] | 2012-07-30 | Week22
[14 empty] | 2012-08-06 | Week23
Formulas:
Mar = [Mar, row above]+7

## Features
Features | Description | WebServices
Pre Booking
Browse packages
Package List | Display packages available based on locations, Date.
Package details | Details of each package
PostBooking
Login | Required for both pre-booking and post-booking.
Retrieve booking | Booking retrievals - summary of all the bookings
Itinerary details | Display daywise details for the booking
List of Attractions available @destination | Showing timeleft for the holiday
Countdown to holiday | Showing timeleft for the holiday
Weather Forecast @ destination | Display weather details based on the location
View messages | Mails/messages received by customer
My views | https://play.google.com/store/apps/details?id=com.thomson.viewmaker
List my views
Capture my views
Add comments to views

## Rezopia-Effort
Customer: |  |  | Customer App for Rezopia |  | Effort | 64.08 | PD
[6 empty] | 3.204 | PM
|  |  | 20 |  |  | 0.2 | 0.5
Estimate
|  | # | Features | UI Design (Wireframes) | Dev | UT | Web services Validation & Integration | Comments
|  | 1 | Req validation |  | 2
|  | 2 | App Arch & BE integration Design |  | 1
|  |  | Test Specs |  | 3
|  |  | Splash |  | 0.5 | 0.1
|  |  | Login (Login functionality, error handling and Reset password). |  | 2 | 0.4 | 1
|  | 3 | Pre Booking
|  | 3.1 | Package List - Display packages available based on locations, Date. |  | 3 | 0.6 | 1.5
|  | 3.2 | Package details - Details of each package |  | 2 | 0.4 | 1
|  | 4 | Post Booking
|  | 4.1 | Retrieve booking - Booking retrievals - summary of all the bookings |  | 2 | 0.4 | 1
|  | 4.2 | Itinerary details-Display daywise details for the booking |  | 1.5 | 0.3 | 0.75
|  | 4.3 | List of Attractions available @destination |  | 1.5 | 0.3 | 0.75
|  | 5 | Countdown to holiday |  | 1 | 0.2
|  | 6 | Weather Forecast @ destination |  | 2 | 0.4 | 1
|  | 7 | View messages |  | 2 | 0.4 | 1
|  | 8 | My views
|  | 8.1 | List my views |  | 2 | 0.4
|  | 8.2 | Capture my views |  | 2 | 0.4
|  | 8.3 | Add comments to views |  | 2 | 0.4
|  |  | Total effort | 0 | 23.5 | 4.7 | 8
|  | 9 | Dev effort Summary
|  |  | iPhone |  | 23.5 | 4.7 | 8
[9 empty] | 0.4 | 0.2
|  |  | Android Phone |  | 11.75 | 4.7 |  | create common W/fs to reduce UX effort
|  |  | Total Dev effort | 58.65
|  | 10 | Testing
| 0.12 |  | Phones | 3.62 |  |  |  | Testing for Android & iPhone | 0.1
| 0.11 |  |  | 0.724 |  |  |  | `+2 iPhones/OS version/formfactors | 0.2
|  |  |  | 1.086 |  |  |  | `+2 Android Phones/OS version/formfactors | 0.3
|  | 11 | Project Management
|  | 12 | Contingency
|  | 13 | Grand total - effort | 64.08 |  |  |  | person days
|  |  |  | 3.204 |  |  |  | person month
Assumptions
|  | 1 | Web services development effort are not included; they are expected to be provided by Rezopia.
|  | 2 | Logos, specific Icons & Images will be provided by Rezopia

## ResourceLoading
Name of the client: Rezopia
Project: Rezopia Customer app
Resources | Grade | M1 | M2 | M3
BA
Architect
UX Designer |  |  |  |  | C | 0
iOS Sr. Dev |  |  |  |  | D | 0
Android Sr. Dev
Sr. Tester
PM
Note on G1: Offshore rate applies